## Standard Timeline
Due Date | Item(s) Due
2021-08-31 | Team Lead Training
2021-09-08 | Examiner Training
2021-09-10 | Examiner Team Training and Work
2021-09-10 | Key Factors Identified by Team and Entered in System by Team Lead
2021-09-11 | 1.1 Entered in APEX
2021-09-14 | 1.2 & 7.4 Entered in APEX
2021-09-17 | First feedback to examiners by Team Lead and Coach
2021-09-17 | Cat 2 & 7.5 in APEX
2021-09-20 | Team Check-in Meeting (Team Lead to Set no later than date listed)
2021-09-24 | Cat 3 & 7.2 in APEX
2021-10-01 | Cat 4 in APEX
2021-10-08 | Team Check-in Meeting (Team Lead to Set no later than date listed)
2021-10-08 | Cat 5 & 7.3 in APEX
2021-10-15 | Cat 6 & 7.1 in APEX
2021-10-17 | Team Lead move Application from IR to Consensus (by noon)
2021-10-18 | Consensus Webinar (review recording)
2021-10-22 | Category Lead generate Consensus Script and load in APEX
2021-10-25 | Consensus Week

## Consensus
Consensus Process & Checklist
Pre-Work |  |  | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4
|  | --> |  |  | --> |  |  | --> |  |  | -->
| Check in with category leads |  |  | Assign Key Theme Guru |  |  | Review previous day - anything team needs to adjust for team norms, process, Q&A |  |  | Review previous day - anything team needs to adjust for team norms, process, Q&A |  |  | Walk the wall to review comments and make notes for site visit and confirm key themes.
| Verify results matrix |  |  | Assign Criteria Cop |  |  | Finished with 4 catergories and 3 results |  |  | Finished with 5 categories and 4 results |  |  | All site visit issues created in system
| Have check-in call with team |  |  | Assign Applicant Advocate |  |  | Check in on Key Theme ideas |  |  | Finished with all categories and scoring. |  |  | All documents desired to be reviewed entered in system
| Site visit final dates to confirm with applicant |  |  | Assign Time Keeper | [8 empty] | If your applicant isn't going to site visit, be sure all comments are feedback ready and key themes written.
|  |  |  | Finished with 2 categories (e.g. 1.1, 1.2, 2.1, 2.2) and 1 (7.4) results category | [8 empty] | Notify director that consensus is finished.

## Site Visit
Site Visit Process & Checklist
Pre-Work |  |  | Schedule & Documents |  |  | Day 0 |  |  | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 (only if needed - rare)
|  | --> |  |  | --> |  |  | --> |  |  | --> |  |  | --> |  |  | -->
| Establish date by 08.30 |  |  | Create schedule with applicant |  |  | Walk the wall |  |  | Opening meeting & comments |  |  | Ensure those not in interviews are working on comments |  |  | Final comments in system |  |  | Only use this is absolutely necessary
| Send Document list by 09.23 |  |  | Finalize document delivery time |  |  | Review schedule |  |  | Remind team to get comments into the system and close Site Visit issues |  |  | Walk the wall -comments |  |  | Key themes in system
| Confirm date with applicant |  |  | Confirm arrival time with team |  |  | Review documents provided |  |  | Walk the wall - comments |  |  | Walk the wall - key themes |  |  | Score items
| Confirm hotel reservations | [8 empty] | Walk the wall - key themes |  |  | Repeat walk the wall until all notes are complete |  |  | Review with team recommendation for recognition level
| Alert IRPE Director of dates | [8 empty] | Assign key themes | [5 empty] | Alert director completed
Collect all paperwork and notes to shred
Destroy all notes and paperwork

## Consensus - No Site Visit
Consensus Process & Checklist
Pre-Work |  |  | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4
|  | --> |  |  | --> |  |  | --> |  |  | -->
| Check in with category leads |  |  | Assign Key Theme Guru |  |  | Review previous day - anything team needs to adjust for team norms, process, Q&A |  |  | Review previous day - anything team needs to adjust for team norms, process, Q&A |  |  | Finished with all categories and scoring.
| Verify results matrix |  |  | Assign Criteria Cop |  |  | Finished with 4 catergories and 3 results |  |  | Finished with 5 categories and 4 results |  |  | Walk the wall to review comments and make notes for site visit and confirm key themes.
| Have check-in call with team |  |  | Assign Applicant Advocate |  |  | Check in on Key Theme ideas | [5 empty] | Final comments in system
| Site visit final dates to confirm with applicant |  |  | Assign Time Keeper | [8 empty] | Key themes in system
|  |  |  | Finished with 2 categories (e.g. 1.1, 1.2, 2.1, 2.2) and 1 (7.4) results category | [8 empty] | Review with team recommendation for recognition level
Collect all paperwork and notes to shred
Destroy all notes and paperwork
Alert director completed